## Sheet1
Task | Resources | 2023-11-30 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | Comments
Create Gantt Chart | MS Excel | [11 empty] | I wasn't working in the week of 25/12/2023 because of holidays | bar: 2023-11-30
Assess user requirements | MS Word/Teams | bar: 2023-11-30
Create the Site map | MS PowerPoint | bar: 2023-11-30
Create Wireframes | MS PowerPoint | bar: 2023-11-30 to 2023-12-04
Review the website designs with another person | MS Teams | bar: 2023-12-11
Create an asset list | MS Word | bar: 2023-12-11
Find assets for the website | Google Chrome/Unsplash.com | bar: 2023-12-11
Edit the assets to fit the website | Adobe Photoshop | bar: 2023-12-18
Gather assets into one folder | bar: 2023-12-18
Create the root folder of the website | bar: 2023-12-18
Create the HTML and CSS files | bar: 2023-12-18
Create the website | MS Visual Studio Code | 2024-01-01: 18h
Test the website | Google Chrome/MS Word | bar: 2024-01-01 to 2024-01-29
Fix any issues that came up | MS Visual Studio Code | bar: 2024-01-01 to 2024-01-29
Review the finished website | MS Word | bar: 2024-02-05